## Slide 1
Shopfloor IT/OT Transformation
3-Year Plan
As of 2026-04-17

## Slide 2
Executive Summary
Vision: stable, single point of integration between shopfloor OT and enterprise IT
Pillar 1 — Unification: 100% of sites on standardized stack (OtOpcUa + ScadaBridge + Redpanda + Snowflake)
Pillar 2 — Analytics/AI: ≤15-min analytics SLO, one "not possible before" use case in production
Pillar 3 — Legacy Retirement: zero remaining bespoke IT/OT paths outside ScadaBridge
Out of scope: operator UX modernization, licensing, VM-level DR, physical network segmentation

## Slide 3
Today's Reality
Split SCADA stack — Aveva System Platform (validated data) + Ignition (KPI), different deployment models
WAN-dependent central Ignition with direct OPC UA sessions to every site's equipment
Multiple concurrent OPC UA sessions to same equipment from 3 different consumers
3 legacy IT/OT integrations running outside ScadaBridge (Delmia DNC, Camstar MES, email notifications)
Fragmented data access — same tag read by different consumers can produce different values

## Slide 4
VISION
"A stable, single point of integration between shopfloor OT and enterprise IT"
Single IT/OT crossing at ScadaBridge central
Canonical equipment model across every surface
Unified Namespace — one data vocabulary from equipment to analytics

## Slide 5
Three Pillars
Unification
100% of sites on standardized stack (OtOpcUa + ScadaBridge + Redpanda + Snowflake)
Analytics / AI
≤15-min analytics SLO, one "not possible before" use case in production
Legacy Retirement
Drive 3 legacy IT/OT integrations to zero

## Slide 6
Enterprise Layout
Primary DC
South Bend Data Center
Largest Sites
Warsaw West, Warsaw North (one cluster per building)
Integrated Sites
Shannon, Galway, TMT, Ponce (single cluster per site)
Not Yet Integrated
Berlin, Winterthur, Jacksonville (Year 2+ onboarding)

## Slide 7
Today's Systems
Aveva System Platform — validated data collection, 2023 R2
Ignition SCADA — KPI monitoring, centrally hosted, Perspective + OPC UA
ScadaBridge — in-house Akka.NET integration layer, already deployed
LmxOpcUa — in-house OPC UA server exposing System Platform objects
Camstar MES — sole enterprise MES
Aveva Historian — sole historian, central-only, permanent retention

## Slide 8
Layered Architecture
Enterprise IT (Camstar, Delmia, Snowflake, Power BI)
IT / OT Boundary
Layer 4: ScadaBridge (IT/OT bridge)
Layer 3: SCADA (System Platform + Ignition)
Layer 2: OtOpcUa (unified OPC UA — equipment + System Platform namespaces)
Layer 1: Equipment (PLCs, controllers, instruments)

## Slide 9
End-to-End Data Flow
Equipment
→
OtOpcUa
→
System Platform / Ignition
→
ScadaBridge
→
Redpanda
→
SnowBridge
→
Snowflake
→
dbt
→
Power BI
A tag read from Warsaw West flows through every layer to reach analytics

## Slide 10
OtOpcUa
Single sanctioned OPC UA access point per site — one session per equipment
Two namespaces: equipment (raw data) + System Platform (processed, from LmxOpcUa)
8 committed core drivers: OPC UA Client, Modbus, AB CIP, AB Legacy, S7, TwinCAT, FOCAS, Galaxy
3-tier driver stability: in-process (Modbus), guarded (S7/CIP), out-of-process (Galaxy/FOCAS)
Tiered cutover: ScadaBridge first, Ignition second, System Platform IO last
Data-path ACL model: 6-level scope, generation-versioned, default-deny

## Slide 11
Analytics Stack
SnowBridge — custom-built machine-data-to-Snowflake upload service
Year 1 source: Aveva Historian SQL; Year 2: add Redpanda/ScadaBridge adapter
Governed selection with blast-radius-based approval workflow
dbt curated layers aligned with canonical model + state vocabulary
≤15-minute analytics SLO
Canonical-state OEE model — strong pillar 2 "not possible before" candidate

## Slide 12
Redpanda EventHub
Self-hosted, central in South Bend (single-cluster HA)
Tiered retention: operational 7d / analytics 30d / compliance 90d
Protobuf schemas in central schemas repo with buf CI
Canonical equipment/production/event model published here
Machine state vocabulary: Running / Idle / Faulted / Starved / Blocked
SASL/OAUTHBEARER auth + prefix ACLs

## Slide 13
3-Year Roadmap
Workstream | Year 1 | Year 2 | Year 3
OtOpcUa | Build + deploy + begin tier 1 | Complete tier 1, begin tier 2 | Complete tier 2+3, steady state
Redpanda | Stand up cluster + schemas repo | Expand topics, replay drill | Steady-state ops
SnowBridge | Build, Historian SQL adapter | Add Redpanda adapter, ship UI | Harden, feature freeze
dbt Layer | Scaffold, first curated model | All domains, OEE model | Not-possible-before use case live
ScadaBridge Ext | Deadband + EventHub producer | Roll to all sites, tune | Steady state
Site Onboarding | Document pattern (no new sites) | Pilot one small site, scale | Complete all remaining sites
Legacy Retirement | Retire first integration | Bulk migration | Drive to zero

## Slide 14
Year 1 Focus
OtOpcUa — evolve LmxOpcUa, 8 core drivers, deploy everywhere, begin tier 1
Redpanda — central cluster, schemas repo, canonical model v1, FANUC CNC pilot
SnowBridge — build in .NET, first adapter (Historian SQL), filtered flow
dbt — scaffold project, first curated model aligned with canonical vocabulary
ScadaBridge — deadband publishing + EventHub producer
Site Onboarding — document lightweight pattern, no new sites Year 1
Legacy Retirement — retire first integration (LEG-002 Camstar) end-to-end

## Slide 15
Pillar 3: Legacy Retirement
LEG-001: Aveva Web API ↔ Delmia DNC — bidirectional, harder (needs ScadaBridge scripts for parse logic)
LEG-002: Aveva Web API ← Camstar MES — Camstar-initiated, easier (ScadaBridge native path exists)
LEG-003: System Platform → custom email service — easier (ScadaBridge email notifications exist)
Historian MSSQL reporting (BOBJ / Power BI) explicitly carved out — not legacy

## Slide 16
Open Coordination Items
Digital Twin
Use cases received (state model, simulation, canonical model). Uses 1 + 3 absorbed into canonical model work. Use case 2 (simulation) exploratory only — full commissioning simulation stays out of scope.
Power BI Migration
Three consumption paths analyzed. Recommended: Path C (hybrid) with Path A as strategic direction. Reporting team conversation pending.

## Slide 17
Non-Goals
Operator UX modernization — deprioritized against the three pillars
Support staffing — other teams
Licensing strategy — not tracked
Orchestrator selection — chosen outside this plan
VM-level DR — out of scope for Redpanda
Physical network segmentation — out of scope

## Slide 18
Asks and Next Steps
Name the integration/operations team that owns consumer cutover planning
Name an owner team for the schemas repo content
Schedule Power BI coordination conversation with reporting team
Assign UNS hierarchy walk owner (Q1-Q2 Year 1)
Assign enterprise shortname for UNS root (currently "ent" placeholder)